## Collated Planned and Complete
Network North Roads Resurfacing Fund - SmartSurvey Reporting Requirements
Note: Please add as many rows as you feel is necessary to highlight the scope and scale of the works being undertaken from Budget 2023 and Network North funding
Local Authority Name: SYMCA
PLANNED WORKS - as at 15/3/24
| Areas / roads where work is planned | Type of works being undertaken on asset group (eg: road resurfacing, bridge repair, culverts maintenance, cycleways, footways etc) | Indicative Cost | Surface area resurfaced (if applicable) m2 | Benefits from it (eg: improved journey times etc)
RRF | Athersley | Carriageway Surface Dressing | 1188.7994 | 880 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Birdwell | Carriageway Surface Dressing | 6285.6879 | 883 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Crane Moor | Carriageway Surface Dressing | 8542.2712 | 5950 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Darfield | Carriageway Surface Dressing | 15660.8306 | 2200 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Monk Bretton | Carriageway Surface Dressing | 24003.7821 | 3372 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Smithies | Carriageway Surface Dressing | 320.3352 | 243 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Thurgoland | Carriageway Surface Dressing | 21797.0287 | 3062 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Wombwell | Carriageway Surface Dressing | 91089.0855 | 12796 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Barnsley | Carriageway Patching | 10836.7354 | 175 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Birdwell | Carriageway Patching | 10779.5327 | 160 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Cudworth | Carriageway Patching | 11370.6274 | 315 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Darton | Carriageway Patching | 14961.6864 | 590 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Gilroyd | Carriageway Patching | 21025.1735 | 180 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Hade Edge | Carriageway Patching | 16337.0937 | 850 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Higham | Carriageway Patching | 15190.4972 | 650 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Hoyland | Carriageway Patching | 22817.5251 | 650 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Middlecliffe | Carriageway Patching | 11526.9815 | 356 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Pilley | Carriageway Patching | 18259.1047 | 950 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Pogmoor | Carriageway Patching | 10314.284 | 38 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Royston | Carriageway Patching | 42476.4437 | 2210 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Wombwell | Carriageway Patching | 24409.54 | 1270 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Worsbrough | Carriageway Patching | 17874.7025 | 930 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Worsbrough Common | Carriageway Patching | 11046.4787 | 230 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Wortley | Carriageway Patching | 15762.5243 | 800 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Barnsley | Carriageway Resurfacing (A Roads) | 374711.2934 | 4220 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Hoyland | Carriageway Resurfacing (A Roads) | 309657.332 | 3500 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | Hoylandswaine | Carriageway Resurfacing (A Roads) | 76087.2301 | 860 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | CDC - programme and location detail subject to final cabinet approval | Major Scheme | 305081.1153 | 10000 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | CDC - programme and location detail subject to final cabinet approval | Re-tread | 203387.4102 | 11000 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | CDC - programme and location detail subject to final cabinet approval | Micro-asphalt | 101693.7051 | 13000 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | CDC - programme and location detail subject to final cabinet approval | Large scale patching | 528807.2665 | 13000 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | CDC - programme and location detail subject to final cabinet approval | Footway schemes | 101693.7051 | 1500 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | CDC - programme and location detail subject to final cabinet approval | Footway Slurry | 203387.4102 | 33000 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | CDC - programme and location detail subject to final cabinet approval | Contingencies | 157944.5611 | - | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
Budget | CDC - programme and location detail subject to final cabinet approval | Major Scheme | 146000 | 4957.9167 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
Budget | CDC - programme and location detail subject to final cabinet approval | Mini schemes | 150000 | 5000 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
Budget | CDC - programme and location detail subject to final cabinet approval | Re-tread | 185000 | 10175 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
Budget | CDC - programme and location detail subject to final cabinet approval | Micro-asphalt | 120000 | 15600 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
Budget | CDC - programme and location detail subject to final cabinet approval | Contingencies | 30817 | - | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | BRAMPTON-EN-LE-MORTHEN TOAD LANE | Road Resurfacing - Unclassified Network | 109259.7167 | 5460 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | CATCLIFFE MAPPINS ROAD | Road Resurfacing - Unclassified Network | 11186.3076 | 500 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | CATCLIFFE VICTORIA STREET | Road Resurfacing - Unclassified Network | 13911.6989 | 435 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | CATCLIFFE OLIVERS WAY | Road Resurfacing - Unclassified Network | 31880.9765 | 575 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | EAST DENE DENE CRESCENT | Road Resurfacing - Unclassified Network | 84611.1965 | 2785 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | KILNHURST CHARLES STREET | Road Resurfacing - Unclassified Network | 59368.785 | 775 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | KILNHURST THOMAS STREET | Road Resurfacing - Unclassified Network | 70544.9232 | 835 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | KIMBERWORTH PARK KENT ROAD | Road Resurfacing - Unclassified Network | 18304.8669 | 665 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | KIMBERWORTH PARK LEYBOURNE ROAD | Road Resurfacing - Unclassified Network | 53897.6637 | 1655 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | MALTBY BEECH ROAD | Road Resurfacing - Unclassified Network | 51636.1991 | 1410 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | MALTBY BYRON ROAD | Road Resurfacing - Unclassified Network | 49829.9155 | 900 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | MALTBY BYFORD ROAD | Road Resurfacing - Unclassified Network | 17287.9299 | 240 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | MALTBY COLERIDGE ROAD | Road Resurfacing - Unclassified Network | 35133.1412 | 630 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | MALTBY TENNYSON ROAD | Road Resurfacing - Unclassified Network | 25423.4263 | 490 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | MOORGATE HALLAM ROAD | Road Resurfacing - Unclassified Network | 146239.4123 | 3165 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | NORTH ANSTON SUFFOLK CLOSE | Road Resurfacing - Unclassified Network | 7443.9792 | 205 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | NORTH ANSTON SUNNYSIDE CLOSE | Road Resurfacing - Unclassified Network | 17176.0668 | 380 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | NORTH ANSTON THE OVAL | Road Resurfacing - Unclassified Network | 71938.127 | 2345 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | WENTWORTH MILL LANE | Road Resurfacing - Unclassified Network | 50846.8525 | 3125 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | WHISTON HALL CLOSE AVENUE | Road Resurfacing - Unclassified Network | 91219.2535 | 2545 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | SWINTON PARK ROAD | Road Resurfacing - Unclassified Network | 116947.7609 | 3595 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
RRF | WATH-UPON-DEARNE BOSWELL ROAD | Road Resurfacing - Unclassified Network | 47584.5185 | 1089 | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
Budget | Rotherham programme definition to be completed | Road Resurfacing - Unclassified Network | 397349 | To be calculated on confirmation of works programme | 2024/2025 Delivery - Improved local road condition, improved safety, improved streetscene, better air quality
COMPLETED WORKS - as at 15/3/24
| Areas / roads where work is planned | Type of works being undertaken on asset group (eg: road resurfacing, bridge repair, culverts maintenance, cycleways, footways etc) | Indicative cost | Surface area resurfaced (if applicable) m2 | Benefits from it (eg: improved journey times etc)
budget | Barugh Green | Carriageway Patching | 18397.7 | 558 | Improved local road condition, improved safety, improved streetscene, better air quality
budget | Bolton upon Dearne | Carriageway Patching | 25417.58 | 800 | Improved local road condition, improved safety, improved streetscene, better air quality
budget | Brierley | Carriageway Patching | 65668.2 | 2265 | Improved local road condition, improved safety, improved streetscene, better air quality
budget | Carlton | Carriageway Patching | 94149.39 | 1910 | Improved local road condition, improved safety, improved streetscene, better air quality
budget | Cubley | Carriageway Patching | 11587.3683 | 82 | Improved local road condition, improved safety, improved streetscene, better air quality
budget | Cudworth | Carriageway Patching | 97461.49 | 600 | Improved local road condition, improved safety, improved streetscene, better air quality
budget | Darfield | Carriageway Patching | 86164.91 | 890 | Improved local road condition, improved safety, improved streetscene, better air quality
budget | Dunford Bridge | Carriageway Patching | 16879.23 | 390 | Improved local road condition, improved safety, improved streetscene, better air quality
budget | Higham | Carriageway Patching | 27833.11 | 732 | Improved local road condition, improved safety, improved streetscene, better air quality
budget | Howbrook | Carriageway Patching | 884.33 | 114 | Improved local road condition, improved safety, improved streetscene, better air quality
budget | Jump | Carriageway Patching | 54088.26 | 667 | Improved local road condition, improved safety, improved streetscene, better air quality
budget | Oxspring | Carriageway Patching | 36534.9 | 1002 | Improved local road condition, improved safety, improved streetscene, better air quality
budget | Redbrook | Carriageway Patching | 66795.12 | 1400 | Improved local road condition, improved safety, improved streetscene, better air quality
budget | Silkstone Common | Carriageway Patching | 24889.3654 | 122 | Improved local road condition, improved safety, improved streetscene, better air quality
budget | Thurnscoe | Carriageway Patching | 29334.75 | 726 | Improved local road condition, improved safety, improved streetscene, better air quality
budget | Wombwell | Carriageway Patching | 93273.93 | 1331 | Improved local road condition, improved safety, improved streetscene, better air quality
budget | Worsbrough | Carriageway Patching | 42021.11 | 1025 | Improved local road condition, improved safety, improved streetscene, better air quality
budget | Wortley | Carriageway Patching | 51053.2563 | 972 | Improved local road condition, improved safety, improved streetscene, better air quality
budget | Great Yorkshire Way | Asphalt preservation | 40000 | 10000 | Improved local road condition, improved safety, improved streetscene, better air quality
budget | CDC - Authority wide | Large scale patching | 300000 | 7500 | Improved local road condition, improved safety, improved streetscene, better air quality
budget | CDC - Windmill Balk / Springwell Lane | Major scheme | 94000 | 3192.0833 | Improved local road condition, improved safety, improved streetscene, better air quality
budget | CDC Wrancarr Lane | Re-tread | 55000 | 3025 | Improved local road condition, improved safety, improved streetscene, better air quality
Improved local road condition, improved safety, improved streetscene, better air quality
budget | Wentworth Rd, Thorpe Hesley | Road Resurfacing | 429000 | Measurements and cost disaggregation to be provided | Improved local road condition, improved safety, improved streetscene, better air quality
budget | Church Lane Dinnington | Road Resurfacing
budget | Warren Vale Rawmarsh | Road Resurfacing
budget | Coach Road, Greasbrough | Classified Road Network
budget | Church St, Greasbrough | Classified Road Network
The plan should include summaries of the additional resurfacing and other work either completed in 2023/24 or scheduled in 2024/25 using the additional funding in Budget 2023 and the further funding confirmed in this letter. This should set out the total volumes of additional work already completed and due to be completed by March 2025; particular roads, communities, or locations that have already benefited from it, or that are due to benefit from it; and the further additional work that will be completed during 2024/25 – again setting out both expected total volumes of additional work and where it is planned